# Meeting Minutes

| Location: | Microsoft Teams, HIT140 2026 Darwin Group 6, General channel (meeting recorded) |
| --- | --- |
| Date: | 13 October 2026 (Meeting 5) |
| Time: Chairperson: Minute Taker: | 2:35 PM (about 7 minutes) Nasid Alve Nasid Alve |
| Absent with apology: | None recorded |
| Absent without apology: | Jahid Hasan, Nahidul Islam Nadim (no apology mentioned during the meeting) |

Progress made since the last meeting

| No | Item | Responsible Person/s | Status/Issues/Remarks |
| --- | --- | --- | --- |
| 1 | Attendance | Md Foysal, Nasid Alve | Only Md Foysal and Nasid Alve attended. Meeting was recorded so absent members can watch it later |
| 2 | LR 2.1 data and EDA (Member 1) | Md Foysal | Completed. OLS summary output (OLS full summary .txt) pushed to GitHub |
| 3 | LR 2.1 modelling (Member 2) | Jahid Hasan | Reported as finished by Md Foysal |
| 4 | LR 2.2 dataset and EDA (Member 3) | Nasid Alve | Completed and code pushed to GitHub. EDA notes for Member 4 included in the repository |
| 5 | LR 2.2 model comparison (Member 4) | Nahidul Islam Nadim | Not yet finished. Nasid Alve guided him the previous night; he has also asked Md Foysal for help |
| 6 | Use of Md Foysal's OLS summary in the report | Nasid Alve, Md Foysal | The .txt file is model output, not report text. The report needs written paragraphs; Nasid Alve to review the summary and confirm if it is enough |

Next deliverables and internal deadlines

| No | Item | Responsible Person/s | Internal Deadlines |
| --- | --- | --- | --- |
| 1 | Finish the LR 2.2 model comparison and coordinate with the team | Nahidul Islam Nadim | Tonight (13 October 2026) |
| 2 | Read Nasid Alve's EDA notes for Member 4 in the repository | Nahidul Islam Nadim | Before starting the model comparison |
| 3 | Watch the meeting recording | Jahid Hasan, Nahidul Islam Nadim | Before the next meeting |
| 4 | Review Md Foysal's OLS summary and give feedback | Nasid Alve | Before the next meeting |
| 5 | Finish each member's report section | All members | 14 October 2026, afternoon |
| 6 | Merge all sections into the final report | Nasid Alve | 14 October 2026, after sections are received |
| 7 | Submit the zip file | Nasid Alve | Target 14 October 2026 night (deadline 15 October 2026, 2:00 PM) |
| 8 | Next team meeting (all members must attend) | All members | 11:30 (time agreed in the meeting) |

Comments :

Only Md Foysal and Nasid Alve attended; Jahid Hasan and Nahidul Islam Nadim were absent, so the meeting was recorded for them to watch later. Md Foysal and Nasid Alve confirmed their parts are complete and pushed to GitHub, and Md Foysal reported that Jahid Hasan's part is also finished. The only remaining task is Nahidul Islam Nadim's LR 2.2 model comparison. Nasid Alve had already guided him and asked him to finish tonight, read the EDA notes left for Member 4, and coordinate with the team. Md Foysal asked whether his OLS summary on GitHub is enough for the report; Nasid Alve noted that the report needs written paragraphs rather than raw output and will review it and reply. Everyone will finish their report section by tomorrow afternoon, after which the report will be merged, aiming to submit tomorrow night. All members must attend the next meeting at 11:30.