# Meeting Minutes

| Location: | Microsoft Teams, HIT140 2026 Darwin Group 6, General channel (meeting recorded) |
| --- | --- |
| Date: | 6 October 2026 |
| Time: Chairperson: Minute Taker: | 1:38 PM Nasid Alve Md Foysal |
| Absent with apology: | None |
| Absent without apology: | None |

Progress made since the last meeting

| No | Item | Responsible Person/s | Status/Issues/Remarks |
| --- | --- | --- | --- |
| 1 | Full match data sheet (104 matches) reviewed and verified | Jahid Hasan | Goals checked against the official group understanding and 12 incorrect scores corrected |
| 2 | Exploratory data analysis (EDA) completed | Jahid Hasan | No missing values. Squad market value difference is the strongest predictor; squad average age difference has almost no relationship with goal difference |
| 3 | Eight variables selected for the analysis | Jahid Hasan | Selected; other members to confirm or swap after reviewing the assessment |
| 4 | Data limitations identified | Jahid Hasan | Squad value and age data came from a secondary source; Transfermarkt data still to be collected |
| 5 | Task order agreed (each task depends on the one before) | All members | Task 1 Jahid Hasan, Task 2 Md Foysal, Task 3 Nasid Alve, Task 4 Nahidul Islam |
| 6 | Work on Tasks 2, 3 and 4 | Md Foysal, Nasid Alve, Nahidul Islam | Not yet started; to begin after reviewing the full assessment |

Next deliverables and internal deadlines

| No | Item | Responsible Person/s | Internal Deadlines |
| --- | --- | --- | --- |
| 1 | Finish Task 1 (collect Transfermarkt data, finalise cleaned data sheet) and send to Md Foysal | Jahid Hasan | 7 October 2026 |
| 2 | Review the full assessment and confirm whether to keep or swap the eight variables | Md Foysal, Nasid Alve, Nahidul Islam | 7 October 2026 |
| 3 | Complete Task 2 using the cleaned data sheet, then pass it to Nasid Alve | Md Foysal | After receiving Task 1 |
| 4 | Complete Task 3, then pass it to Nahidul Islam | Nasid Alve | After receiving Task 2 |
| 5 | Complete Task 4 | Nahidul Islam | After receiving Task 3 |
| 6 | Confirm availability for the next meeting | Nasid Alve | 7 October 2026, after 12:00 PM |
| 7 | Next team meeting on Microsoft Teams | All members | 7 October 2026, 9:30 PM |

Comments :

Jahid Hasan reported on Task 1: he checked the 104 match data sheet, completed the EDA and selected eight variables (FIFA ranking difference, squad market value difference, squad average age difference, World Cup based result difference, qualifying goal difference, home/away and host advantage difference, confederation index difference and rest days difference). He asked whether anyone wanted to swap any variable. Because Nahidul Islam, Nasid Alve and Md Foysal had not yet reviewed the assessment, no decision was made, and the team will decide once they start work. The team agreed to a sequential workflow: Jahid Hasan passes his cleaned data sheet to Md Foysal, who passes his work to Nasid Alve, who passes his to Nahidul Islam. Host nations (USA, Mexico, Canada) had no qualifying campaign, so a qualifying goal difference value was assigned for them. Jahid Hasan will send his sheet on 7 October rather than tonight. Md Foysal joined about five minutes after the start. The team confirmed that the meeting minutes form is required for this assessment. The next meeting was set for 7 October 2026 at 9:30 PM; Nasid Alve will confirm his availability after 12:00 PM.