# Meeting Minutes

| Location: | Microsoft Teams, HIT140 2026 Darwin Group 6, General channel (meeting recorded) |
| --- | --- |
| Date: | 29 September 2026 |
| Time: Chairperson: Minute Taker: | 9:30 PM Nasid Alve Md Foysal |
| Absent with apology: | None |
| Absent without apology: | Jahid Hasan |

Progress made since the last meeting

| No | Item | Responsible Person/s | Status/Issues/Remarks |
| --- | --- | --- | --- |
| 1 | Attendance and start of meeting | Jahid Hasan | Did not join; team waited 30 minutes and Nahidul Islam called him several times without an answer, so the meeting started without him |
| 2 | Task 1 cleaned data sheet from the last meeting | Jahid Hasan | Receipt not confirmed because Jahid Hasan was absent |
| 3 | Second assessment requirements reviewed | Nasid Alve, Md Foysal, Nahidul Islam | Code and a four-page report only, no presentation. Submit a zip file with a text file containing the GitHub link and the report as a docx. Last assessment of the unit, worth 50% |
| 4 | Submission deadline confirmed | Nasid Alve | 15 October 2026, 2:00 PM. Team to finish work by 12 or 13 October and submit one day early |
| 5 | Minutes requirement confirmed | All members | Seven meetings with minutes forms are required; this was meeting 1 of 7 |

Next deliverables and internal deadlines

| No | Item | Responsible Person/s | Internal Deadlines |
| --- | --- | --- | --- |
| 1 | Divide the assessment into four sections and post them on Teams | Nasid Alve | Tonight after 12:00 AM (night of 7 October 2026) |
| 2 | Select a task from the posted sections | All members | After the tasks are posted |
| 3 | Create the GitHub repository for this assessment and invite all members | Md Foysal | After members share usernames |
| 4 | Share GitHub usernames with Md Foysal and accept the invitation | Nasid Alve, Nahidul Islam, Jahid Hasan | After repository is created |
| 5 | Fill the minutes form for each required meeting (Nasid Alve takes the first; Md Foysal agreed to take some later) | All members | After each meeting |
| 6 | Complete code and four-page report | All members | 12 or 13 October 2026 |
| 7 | Submit a zip file (text file with GitHub link and report docx) | All members | 15 October 2026, 2:00 PM (aim for 14 October) |
| 8 | Next team meeting | All members | Not yet set |

Comments :

Jahid Hasan did not join, so the meeting started without him after a 30 minute wait. Nasid Alve confirmed the second assessment is the last for the unit (50%) and requires only code and a four page report, with no presentation, submitted as a zip file containing a text file with the GitHub link and the report. The deadline is 15 October 2026 at 2:00 PM. Because the previous assessment was submitted late, the team agreed to finish by 12 or 13 October and submit one day early. Nasid Alve will divide the work into four sections and post them on Teams after midnight, and each member will choose a task. Seven meetings with minutes forms are required, which means three members will complete two forms and one member one. Nasid Alve will complete the first, and Md Foysal agreed to take some later. Md Foysal will create the GitHub repository and the other members will send him their usernames and accept the invitation. No date was set for the next meeting.