# Meeting Minutes

| Location: | Microsoft Teams, HIT140 2026 Darwin Group 6, General channel (meeting recorded) |
| --- | --- |
| Date: | 13 October 2026 |
| Time: Chairperson: Minute Taker: | 11:30 PM Nasid Alve Jahid Hasan |
| Absent with apology: | None |
| Absent without apology: | None |

Progress made since the last meeting

| No | Item | Responsible Person/s | Status/Issues/Remarks |
| --- | --- | --- | --- |
| 1 | Nasid Alve’s part of the project | Nasid Alve | Done. The EDA instructions for Nahidul Islam are in his GitHub folder |
| 2 | Remaining work for Md Foysal and Jahid Hasan | Md Foysal, Jahid Hasan | Md Foysal said no work was left on his side and Jahid’s side. Nasid Alve said the reports, the merge and the AI Declaration Form still remain |
| 3 | Nahidul Islam’s part and report | Nahidul Islam | In progress. He has read the GitHub files and the EDA instructions. He apologised for missing Meeting 5 because of work. He expects to finish and upload to GitHub on 14 October |
| 4 | Jahid Hasan’s report section | Jahid Hasan | In progress. Will be finished by the morning of 14 October |
| 5 | Meeting minutes for the last two meetings (Meetings 5 and 6) | Jahid Hasan | Jahid Hasan agreed to write them |
| 6 | AI Declaration Form | All members | Not started. It is like the previous one: it needs signatures and the link to the AI chats. Nasid Alve will look into it. Md Foysal said only the link is needed |
| 7 | Report format | All members | One merged document with one part for each member (four parts) |

Next deliverables and internal deadlines

| No | Item | Responsible Person/s | Internal Deadlines |
| --- | --- | --- | --- |
| 1 | Finish own report and upload it to GitHub. Tell the team when finished; if not finished, announce another meeting within 30 minutes | Nahidul Islam | 14 October 2026, about 7:00 PM to 9:00 PM |
| 2 | Finish own report section | Jahid Hasan | Morning of 14 October 2026 |
| 3 | Finish own report sections so they can be merged | Nasid Alve, Md Foysal | Before merging (no date set) |
| 4 | Merge the four report parts into one document | All members | After all parts are finished |
| 5 | Complete the AI Declaration Form (signatures and AI chat link) | Nasid Alve, all members | After the reports are finished |
| 6 | Write meeting minutes for Meetings 5 and 6 | Jahid Hasan | No date set in the meeting |
| 7 | Hold the last team meeting on Microsoft Teams after all work is finished (Thursday proposed; time to be decided) | All members | After all work is finished, Thursday 15 October 2026 |
| 8 | Submit the assignment | All members | Before 2:00 PM on Thursday 15 October 2026 |

Comments :

All four members attended: Nasid Alve, Jahid Hasan, Nahidul Islam and Md Foysal (Md Foysal was on mute for the first part of the call). Nasid Alve said the fifth meeting had been held earlier while Jahid Hasan and Nahidul Islam were absent, and told Nahidul Islam to watch the recording. Nahidul Islam apologised, said he was busy with work, and said he had checked GitHub and part of the recording. He is working on his report and expects to finish it and upload it to GitHub on 14 October between about 7:00 PM and 9:00 PM; if he cannot, he will tell the team and a meeting will be announced within 30 minutes. Jahid Hasan said his report would be finished by the morning of 14 October. Nasid Alve said the AI Declaration Form must also be done; it is like the previous one and needs signatures and the AI chat link, and he will look into it. Md Foysal said little work was left, but Nasid Alve explained that the reports, the merge and the declaration form still take time, as in the last assessment. The team agreed that the final report will be one merged document with one part for each member. Nasid Alve asked Jahid Hasan to write the minutes for the last two meetings and Jahid agreed. The team agreed to hold one more meeting after all work is finished and to set an internal deadline once Nahidul Islam knows when he will finish. Meeting in the evening (7 to 10 PM) or during the day was discussed, because Md Foysal and Jahid Hasan preferred the daytime; the team settled on Thursday for the final meeting, because the assignment must be submitted before 2:00 PM on Thursday 15 October. Nobody had any further questions. These minutes were prepared by Jahid Hasan from the Teams meeting recording and transcript.