# Meeting Minutes

| Location: | Microsoft Teams - HIT140 2026 Darwin Group 6, General channel (meeting recorded) |
| --- | --- |
| Date: | 13 October 2026 |
| Time: Chairperson: Minute Taker: | 11:30 PM Nasid Alve Nahidul Islam |
| Absent with apology: | None |
| Absent without apology: | None |

Progress made since the last meeting

| No | Item | Responsible Person/s | Status/Issues/Remarks |
| --- | --- | --- | --- |
| 1 | Previous meeting instructions reviewed by Nahidul Islam after missing Meeting 5 | Nahidul Islam | Reviewed the GitHub files and part of the previous meeting recording; confirmed that he understood the instructions. |
| 2 | LR 2.2 EDA work and modelling instructions prepared for Nahidul | Nasid Alve | EDA section completed and instructions were already available in GitHub for Nahidul to follow. |
| 3 | Individual Assessment 3 work status reviewed | All members | Most technical work was completed; remaining work focused on Nahidul's section, report completion, merging and final submission tasks. |
| 4 | Nahidul's assigned modelling/report work in progress | Nahidul Islam | Working on the assigned section and planned to finish and upload it to GitHub by the following evening. |
| 5 | Jahid's report/work nearing completion | Jahid Hasan | Expected to finish by the morning of 14 October 2026. |
| 6 | Final submission requirements confirmed | All members | One merged report, AI Usage Declaration Form with signatures and AI conversation links, and final submission checks remain. |

Next deliverables and internal deadlines

| No | Item | Responsible Person/s | Internal Deadlines |
| --- | --- | --- | --- |
| 1 | Complete Nahidul's assigned LR 2.2 modelling/report work and upload it to GitHub | Nahidul Islam | 14 October 2026, around 7:00 PM to 8:00 PM |
| 2 | Complete own report section | Jahid Hasan | 14 October 2026, morning |
| 3 | Finalise all individual report sections and notify the team when complete | All members | 14 October 2026 |
| 4 | Merge all four members' report sections into one final report document | All members | After all sections are complete, before submission |
| 5 | Complete the AI Usage Declaration Form, add signatures and provide relevant AI conversation links | All members | Before final submission |
| 6 | Review the final submission package and confirm the report is ready | All members | Before 15 October 2026, 2:00 PM |
| 7 | Hold the final team meeting after all remaining work is completed | All members | To be scheduled after completion of work and before/around submission |
| 8 | Submit Assessment 3 | All members | 15 October 2026, before 2:00 PM |

Comments:

The third meeting focused on finalising HIT140 Assessment 3 and setting internal deadlines before the submission deadline. Nahidul Islam explained that he had missed the previous meeting because of other work but had since reviewed the GitHub files and part of the previous meeting to understand the instructions. Nasid Alve confirmed that his EDA section was already completed and that instructions for Nahidul's modelling work were available in the repository. Nahidul planned to complete his remaining work and upload it to GitHub by the evening of 14 October, while Jahid Hasan expected to finish his section by the morning.

The team confirmed that the final report must be submitted as one merged document containing the work of all four members, rather than as separate reports. Md Foysal recommended setting an internal deadline to avoid last-minute delays. The group also confirmed that the AI Usage Declaration Form must be completed with signatures and relevant AI conversation links. One final meeting will be held after the remaining work is finished. The group confirmed that Assessment 3 must be submitted before 2:00 PM on 15 October 2026.